## Executive Dashboard
AI-Assisted Incident Management - Executive Dashboard
AI Incident Triage & Response Coordinator ¦ 16-week implementation plan
Program KPI | Baseline | Target |  | Phase | Weeks | Primary Outcome | Planned Status
MTTR | 120 min | 84 min |  | Discovery & Design | W1-W2 | Requirements, architecture, integrations, governance, success metrics | Planned
Ownership Identification | 20 min | < 5 min |  | Prototype Development | W3-W5 | MVP: incident summary, ownership recommendation, runbook search | Planned
Context Gathering | 30 min | < 3 min |  | Sev-2 Pilot | W6-W8 | Controlled pilot, accuracy and trust validation, MTTR measurement | Planned
Executive Updates | 15 min | < 2 min |  | Production Rollout | W9-W12 | Sev-1 and Sev-2 rollout, training, support and controls | Planned
RCA Creation | 4 hrs | < 30 min |  | Optimization | W13-W16 | RCA drafting, timeline scribing, analytics and executive dashboard | Planned
Escalation Accuracy | 70% | > 90%
Runbook Utilization | 40% | > 80%
Health Measure | Current |  | Leadership Control Snapshot
Total roadmap records | 54 |  | Program Guardrail | AI recommends only; humans approve all production actions
Critical-path records | 33 |  | Pilot Scope | Sev-2 incidents in shadow and assisted modes
Tasks complete | 0 |  | Pilot Exit | Recommendation accuracy >= 80% plus positive responder feedback
Tasks blocked | 0 |  | Security Model | Read-only integrations, RBAC and auditable recommendations
Open Red risks | 6 |  | Production Scope | Controlled Sev-1 and Sev-2 enablement after pilot approval
Gates ready | 0 |  | Success Measure | Operational outcomes, not AI usage alone

## Executive Roadmap
AI-Assisted Incident Management - Executive Roadmap
Progressive delivery from discovery through controlled production rollout and optimization
Phase | Weeks | Milestone | Primary Outcomes | Capabilities Introduced | Approval Gate | Gate Owner | Human Control | Planned Status
Discovery & Design | W1-W2 | Design Ready | Requirements, architecture, integrations, governance, success metrics | Scope, architecture, baselines and controls | GATE-DESIGN | Steering Committee | Human approval required for all production actions | Planned
Prototype Development | W3-W5 | MVP Ready for Pilot | MVP: incident summary, ownership recommendation, runbook search | Summarization, ownership and runbook search | GATE-MVP | Steering Committee | Human approval required for all production actions | Planned
Sev-2 Pilot | W6-W8 | Pilot Success | Controlled pilot, accuracy and trust validation, MTTR measurement | Sev-2 recommendations in shadow/assisted mode | GATE-PILOT | Steering Committee | Human approval required for all production actions | Planned
Production Rollout | W9-W12 | Production Accepted | Sev-1 and Sev-2 rollout, training, support and controls | Sev-1 and Sev-2 production enablement | GATE-PROD | Executive Sponsor / SRE | Human approval required for all production actions | Planned
Optimization | W13-W16 | Program Complete | RCA drafting, timeline scribing, analytics and executive dashboard | RCA, timeline scribing, analytics and model governance | GATE-CLOSE | Executive Sponsor | Human approval required for all production actions | Planned

## Detailed Program Tracker
Detailed Program Tracker
Integrated execution plan. AI provides recommendations only; production actions remain human-approved.
Month | Phase | Task ID | Workstream | Task / Milestone | Owner | Type | Start Wk | Duration | End Wk | Predecessors | Critical Path | Status | Deliverable / Evidence | % Complete | RAG | Actual Start Wk | Forecast Finish Wk | Actual Finish Wk | Variance (Wks) | TPM Notes / Recovery Plan
M1 | Program Governance | PM-01 | Program Management | Program kickoff, charter, decision rights and operating cadence | TPM | Task | 1 | 1 | 1 |  | No | Not Started | Approved charter and governance calendar | 0 | Grey
M1 | Program Governance | PM-02 | Program Management | Stand up RAID, dependency, decision and action logs | TPM | Task | 1 | 1 | 1 | PM-01 | No | Not Started | Program controls active | 0 | Grey
M1-M4 | Program Governance | PM-03 | Program Management | Weekly delivery review and bi-weekly steering committee | TPM | Recurring | 1 | 16 | 16 | PM-01 | No | Not Started | Status reports and decision log | 0 | Grey
M1-M4 | Program Governance | PM-04 | Program Management | Monthly KPI and value-realization review | TPM / SRE Lead | Recurring | 4 | 13 | 16 | PM-01 | No | Not Started | KPI scorecard | 0 | Grey
M1 | Discovery & Design | DD-01 | Incident Process | Review Sev-1 and Sev-2 incident lifecycle and pain points | TPM / SRE | Task | 1 | 1 | 1 | PM-01 | Yes | Not Started | Current-state process map | 0 | Grey
M1 | Discovery & Design | DD-02 | Data & Knowledge | Analyze historical incidents, RCAs and problem records | SRE / Data Analyst | Task | 1 | 2 | 2 | DD-01 | No | Not Started | Historical incident analysis | 0 | Grey
M1 | Discovery & Design | DD-03 | Architecture | Inventory monitoring, incident, CMDB, change and knowledge integrations | AI Architect | Task | 1 | 2 | 2 | DD-01 | Yes | Not Started | Integration inventory | 0 | Grey
M1 | Discovery & Design | DD-04 | Security | Define read-only access, RBAC, audit logging and data-handling controls | Security Lead | Task | 1 | 2 | 2 | DD-03 | Yes | Not Started | Security control design | 0 | Grey
M1 | Discovery & Design | DD-05 | Product | Define personas, use cases, in-scope and out-of-scope boundaries | TPM / SRE | Task | 1 | 1 | 1 | DD-01 | No | Not Started | Approved scope | 0 | Grey
M1 | Discovery & Design | DD-06 | Measurement | Baseline MTTR, ownership, context, comms, RCA and runbook metrics | SRE / TPM | Task | 1 | 2 | 2 | DD-02 | Yes | Not Started | Baseline KPI report | 0 | Grey
M1 | Discovery & Design | DD-07 | AI Governance | Define human-in-the-loop, confidence, evidence and audit requirements | Security / SRE | Task | 2 | 1 | 2 | DD-04 | Yes | Not Started | Responsible AI controls | 0 | Grey
M1 | Discovery & Design | DD-08 | Architecture | Complete target architecture and model/vendor decision | AI Architect | Task | 2 | 1 | 2 | DD-03, DD-04 | No | Not Started | Approved architecture | 0 | Grey
M1 | Discovery & Design | DD-09 | Program Management | Approve requirements, architecture and success metrics | Steering Committee | Gate | 2 | 1 | 2 | DD-06, DD-07, DD-08 | Yes | Not Started | Design approval | 0 | Grey
M1 | Discovery & Design | GATE-DESIGN | Program Management | DESIGN READY | Steering Committee | Gate | 2 | 1 | 2 | DD-09 | Yes | Not Started | Authorization to build MVP | 0 | Grey
M1 | Prototype Development | PV-01 | Platform | Provision isolated AI development and test environment | AI Engineering | Task | 3 | 1 | 3 | GATE-DESIGN | Yes | Not Started | Secure test environment | 0 | Grey
M1 | Prototype Development | PV-02 | Integrations | Connect incident platform and monitoring sources read-only | Integration Engineering | Task | 3 | 2 | 4 | PV-01 | Yes | Not Started | Incident and alert connectors | 0 | Grey
M1 | Prototype Development | PV-03 | Knowledge | Ingest approved CMDB, runbooks, RCAs and dependency maps | Knowledge Manager | Task | 3 | 2 | 4 | PV-01 | Yes | Not Started | Curated knowledge index | 0 | Grey
M1 | Prototype Development | PV-04 | AI Engineering | Build incident context aggregation and summarization | AI Engineering | Task | 3 | 2 | 4 | PV-02 | Yes | Not Started | Incident context summary | 0 | Grey
M1 | Prototype Development | PV-05 | AI Engineering | Build ownership and on-call recommendation capability | AI Engineering | Task | 3 | 2 | 4 | PV-02, PV-03 | Yes | Not Started | Resolver recommendation | 0 | Grey
M1-M2 | Prototype Development | PV-06 | AI Engineering | Build runbook and historical incident discovery | AI Engineering | Task | 4 | 2 | 5 | PV-03 | No | Not Started | Evidence-linked recommendations | 0 | Grey
M1-M2 | Prototype Development | PV-07 | AI Engineering | Add confidence scoring, citations and evidence display | AI Engineering | Task | 4 | 2 | 5 | PV-04, PV-05 | Yes | Not Started | Transparent AI output | 0 | Grey
M1-M2 | Prototype Development | PV-08 | Security | Perform privacy, prompt-injection and access-control tests | Security / AI Engineering | Task | 4 | 2 | 5 | PV-07 | Yes | Not Started | Security test report | 0 | Grey
M1-M2 | Prototype Development | PV-09 | Testing | Create benchmark set and accuracy evaluation harness | QA / SRE | Task | 4 | 2 | 5 | DD-02 | Yes | Not Started | Evaluation dataset | 0 | Grey
M2 | Prototype Development | PV-10 | Testing | Execute MVP functional, quality and hallucination testing | QA / SRE | Task | 5 | 1 | 5 | PV-06, PV-08, PV-09 | Yes | Not Started | MVP test report | 0 | Grey
M2 | Prototype Development | GATE-MVP | Program Management | MVP READY FOR PILOT | Steering Committee | Gate | 5 | 1 | 5 | PV-10 | Yes | Not Started | Pilot authorization | 0 | Grey
M2 | Sev-2 Pilot | PL-01 | Pilot Readiness | Select pilot services, Sev-2 incidents and responder cohort | TPM / SRE | Task | 5 | 1 | 5 | GATE-MVP | No | Not Started | Pilot scope and roster | 0 | Grey
M2 | Sev-2 Pilot | PL-02 | Change & Adoption | Train incident commanders and SRE responders | Change Lead | Task | 6 | 1 | 6 | PL-01 | No | Not Started | Training completion | 0 | Grey
M2 | Sev-2 Pilot | PL-03 | Operations | Launch shadow-mode Sev-2 pilot | SRE Lead | Task | 6 | 1 | 6 | PL-02 | Yes | Not Started | Shadow pilot live | 0 | Grey
M2 | Sev-2 Pilot | PL-04 | Measurement | Measure ownership, context, MTTR and recommendation accuracy | TPM / Data Analyst | Recurring | 6 | 3 | 8 | PL-03 | Yes | Not Started | Weekly pilot scorecard | 0 | Grey
M2 | Sev-2 Pilot | PL-05 | AI Quality | Review false positives, hallucinations and confidence calibration | AI Engineering / SRE | Recurring | 6 | 3 | 8 | PL-03 | Yes | Not Started | Quality findings | 0 | Grey
M2 | Sev-2 Pilot | PL-06 | Adoption | Collect responder feedback and acceptance data | Change Lead | Recurring | 6 | 3 | 8 | PL-03 | No | Not Started | Adoption feedback | 0 | Grey
M2 | Sev-2 Pilot | PL-07 | Operations | Enable assisted mode with mandatory human validation | SRE Lead | Task | 7 | 1 | 7 | PL-05 | Yes | Not Started | Assisted pilot live | 0 | Grey
M2 | Sev-2 Pilot | PL-08 | Security | Review audit evidence and access logs | Security Lead | Task | 7 | 1 | 7 | PL-07 | No | Not Started | Pilot control report | 0 | Grey
M2 | Sev-2 Pilot | PL-09 | Program Management | Pilot retrospective and remediation actions | TPM | Task | 8 | 1 | 8 | PL-04, PL-05, PL-06 | No | Not Started | Pilot retrospective | 0 | Grey
M2 | Sev-2 Pilot | GATE-PILOT | Program Management | PILOT SUCCESS: accuracy >=80% and positive responder feedback | Steering Committee | Gate | 8 | 1 | 8 | PL-08, PL-09 | Yes | Not Started | Production rollout authorization | 0 | Grey
M3 | Production Rollout | PR-01 | Platform | Harden availability, capacity, monitoring and support model | AI Engineering / SRE | Task | 9 | 2 | 10 | GATE-PILOT | Yes | Not Started | Production-ready platform | 0 | Grey
M3 | Production Rollout | PR-02 | Integrations | Complete production connectors and data-quality monitoring | Integration Engineering | Task | 9 | 2 | 10 | GATE-PILOT | Yes | Not Started | Production integrations | 0 | Grey
M3 | Production Rollout | PR-03 | Security | Complete production security, compliance and audit approval | Security Lead | Task | 9 | 2 | 10 | GATE-PILOT | Yes | Not Started | Security sign-off | 0 | Grey
M3 | Production Rollout | PR-04 | Change & Adoption | Finalize SOPs, training, communications and support model | Change Lead / TPM | Task | 9 | 2 | 10 | GATE-PILOT | No | Not Started | Operational readiness pack | 0 | Grey
M3 | Production Rollout | PR-05 | Deployment | Roll out to Sev-2 incidents | SRE Lead | Task | 10 | 1 | 10 | PR-01, PR-02, PR-03 | Yes | Not Started | Sev-2 production enablement | 0 | Grey
M3 | Production Rollout | PR-06 | Deployment | Controlled rollout to Sev-1 incidents | SRE Lead | Task | 11 | 1 | 11 | PR-05 | Yes | Not Started | Sev-1 production enablement | 0 | Grey
M3 | Production Rollout | PR-07 | Operations | Hypercare and daily quality review | SRE / AI Engineering | Task | 10 | 3 | 12 | PR-05 | Yes | Not Started | Hypercare evidence | 0 | Grey
M3 | Production Rollout | PR-08 | Measurement | Validate production KPI movement and adoption | TPM / Data Analyst | Task | 11 | 2 | 12 | PR-05 | No | Not Started | Production KPI report | 0 | Grey
M3 | Production Rollout | PR-09 | Operations | Transition support, incident ownership and escalation model | SRE Lead | Task | 12 | 1 | 12 | PR-07 | No | Not Started | Support acceptance | 0 | Grey
M3 | Production Rollout | GATE-PROD | Program Management | PRODUCTION ACCEPTED | Executive Sponsor / SRE | Gate | 12 | 1 | 12 | PR-03, PR-08, PR-09 | Yes | Not Started | Production acceptance | 0 | Grey
M4 | Optimization | OP-01 | AI Engineering | Build real-time incident timeline scribing | AI Engineering | Task | 13 | 2 | 14 | GATE-PROD | No | Not Started | Real-time incident timeline | 0 | Grey
M4 | Optimization | OP-02 | AI Engineering | Build RCA and action-item drafting | AI Engineering | Task | 13 | 2 | 14 | GATE-PROD | No | Not Started | Evidence-linked RCA draft | 0 | Grey
M4 | Optimization | OP-03 | Analytics | Build trend analytics and executive dashboards | Data / BI | Task | 13 | 2 | 14 | GATE-PROD | No | Not Started | Executive dashboard | 0 | Grey
M4 | Optimization | OP-04 | Knowledge | Establish content curation and knowledge freshness process | Knowledge Manager | Task | 13 | 2 | 14 | GATE-PROD | Yes | Not Started | Knowledge governance SOP | 0 | Grey
M4 | Optimization | OP-05 | Model Governance | Establish quarterly model review, drift monitoring and retraining | AI Engineering / Security | Task | 14 | 2 | 15 | GATE-PROD | Yes | Not Started | Model governance process | 0 | Grey
M4 | Optimization | OP-06 | Testing | Validate RCA quality, timeline accuracy and analytics | QA / SRE | Task | 15 | 1 | 15 | OP-01, OP-02, OP-03 | No | Not Started | Optimization test report | 0 | Grey
M4 | Optimization | OP-07 | Value Realization | Complete final KPI, adoption and business-outcome assessment | TPM / SRE | Task | 15 | 2 | 16 | OP-06 | Yes | Not Started | Benefits realization report | 0 | Grey
M4 | Optimization | OP-08 | Program Management | Operational handoff and lessons learned | TPM | Task | 16 | 1 | 16 | OP-04, OP-05, OP-07 | No | Not Started | Closure and handoff report | 0 | Grey
M4 | Optimization | GATE-CLOSE | Program Management | PROGRAM COMPLETE | Executive Sponsor | Gate | 16 | 1 | 16 | OP-08 | Yes | Not Started | Program closure | 0 | Grey

## Capability Tracker
AI Capability & Control Tracker
Capability delivery, data sources, outputs and mandatory human controls
Capability | Phase | Primary Data Sources | AI Output | User | Confidence Required | Evidence Displayed | Human Approval | Delivery Status | Owner
Incident Context Aggregation | Prototype | Alerts, logs, metrics, traces, dependencies | Single incident context summary | Incident Commander | Yes | Yes | Required for actions | Not Started | AI Engineering
Ownership Recommendation | Prototype | CMDB, service ownership, on-call schedules | Primary and secondary resolver teams | Incident Commander | Yes | Yes | Required | Not Started | AI Engineering / SRE
Change Correlation | Production | Deployments, infrastructure and configuration changes | Recent-change candidates | SRE Engineers | Yes | Yes | Required | Not Started | Integration Engineering
Historical Incident Discovery | Prototype | Incidents, RCAs, problem records | Similar incidents and prior mitigations | SRE Engineers | Yes | Yes | Required | Not Started | Knowledge Manager
Runbook Discovery | Prototype | Approved runbooks and troubleshooting guides | Relevant runbook suggestions | SRE Engineers | Yes | Yes | Required | Not Started | Knowledge Manager
Executive Communications | Production | Incident context and impact data | Draft status and leadership updates | Leadership | Yes | Yes | Incident Commander approval | Not Started | TPM / SRE
RCA Drafting | Optimization | Timeline, logs, decisions and actions | Draft RCA and action items | SRE / App Teams | Yes | Yes | Engineering review | Not Started | AI Engineering
Incident Timeline Scribing | Optimization | Incident events, decisions and status updates | Real-time incident timeline | Incident Commander | Yes | Yes | Incident Commander review | Not Started | AI Engineering

## Gate Readiness
Milestone & Gate Readiness
Summary is calculated from the Gate Criteria Checklist.
Gate ID | Decision Point | Target Week | Approver | # Criteria | # Complete | Readiness % | RAG | Decision / Notes | Evidence Owner
GATE-DESIGN | DESIGN READY | 2 | Steering Committee | 5 | 0 | 0% | Not Started |  | TPM
GATE-MVP | MVP READY FOR PILOT | 5 | Steering Committee | 5 | 0 | 0% | Not Started |  | TPM
GATE-PILOT | PILOT SUCCESS | 8 | Steering Committee | 5 | 0 | 0% | Not Started |  | TPM
GATE-PROD | PRODUCTION ACCEPTED | 12 | Executive Sponsor / SRE | 5 | 0 | 0% | Not Started |  | TPM
GATE-CLOSE | PROGRAM COMPLETE | 16 | Executive Sponsor | 5 | 0 | 0% | Not Started |  | TPM
RAG Logic
Not Started | 0 criteria complete
Red | 1%-74% complete
Amber | 75%-99% complete
Green | 100% complete

## Gate Criteria Checklist
Gate Exit-Criteria Checklist
Update the Status and Evidence Link columns. Gate Readiness recalculates automatically.
Gate ID | Exit Criterion | Owner | Evidence / Artefact | Source | Status | Comments / Evidence Link
GATE-DESIGN | Requirements and use cases approved | TPM | Required approval or test evidence | Program Plan | Not Started
GATE-DESIGN | Architecture and integrations approved | AI Architect | Required approval or test evidence | Program Plan | Not Started
GATE-DESIGN | Baseline KPIs established | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-DESIGN | Human-in-the-loop controls approved | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-DESIGN | Read-only access design approved | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-MVP | MVP capabilities demonstrated | AI Engineering | Required approval or test evidence | Program Plan | Not Started
GATE-MVP | Benchmark dataset approved | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-MVP | Accuracy evaluation completed | QA Lead | Required approval or test evidence | Program Plan | Not Started
GATE-MVP | Security and access tests passed | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-MVP | Evidence and confidence displayed | AI Engineering | Required approval or test evidence | Program Plan | Not Started
GATE-PILOT | Recommendation accuracy >= 80% | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PILOT | Positive responder feedback | Change Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PILOT | No unauthorized production action | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PILOT | Audit evidence complete | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PILOT | Pilot KPI report accepted | TPM | Required approval or test evidence | Program Plan | Not Started
GATE-PROD | Production security approval | Security Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PROD | Sev-1 and Sev-2 workflows enabled | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PROD | Training and support model complete | Change Lead | Required approval or test evidence | Program Plan | Not Started
GATE-PROD | Production KPI review complete | TPM | Required approval or test evidence | Program Plan | Not Started
GATE-PROD | SRE operational acceptance | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-CLOSE | MTTR target assessed | SRE Lead | Required approval or test evidence | Program Plan | Not Started
GATE-CLOSE | Ownership and context targets assessed | TPM | Required approval or test evidence | Program Plan | Not Started
GATE-CLOSE | RCA and communications targets assessed | TPM | Required approval or test evidence | Program Plan | Not Started
GATE-CLOSE | Model governance and knowledge process accepted | Security / SRE | Required approval or test evidence | Program Plan | Not Started
GATE-CLOSE | Operational handoff complete | Executive Sponsor | Required approval or test evidence | Program Plan | Not Started

## Critical Dependencies
Critical Dependency Register
Technical, data, security, operational and adoption dependencies.
ID | Category | Dependency | Provider / Owner | Blocks Task | Needed By Wk | Latest Start Wk | Urgency | Capability / Phase | Mitigation / Action | Status | RAG
D-01 | Technical | Read-only API access to monitoring tools | Monitoring Platform Owner | PV-02 | 3 | 3 | Start at kickoff | All | Confirm API scopes and rate limits; use test tenant | Not Started | Red
D-02 | Technical | Incident platform integration and event schema | ServiceNow/PagerDuty Owner | PV-02 | 3 | 3 | Start at kickoff | All | Agree incident fields, webhooks and sandbox access | Not Started | Red
D-03 | Data | CMDB and service ownership data quality | CMDB Owner | PV-05 | 3 | 3 | Month 1 | Ownership | Data profiling, owner attestation and exception queue | Not Started | Red
D-04 | Knowledge | Runbooks, RCAs and incident records are searchable and current | Knowledge Manager | PV-03 | 3 | 3 | Month 1 | Knowledge | Content curation, metadata standards and freshness SLA | Not Started | Amber
D-05 | Security | RBAC, privacy, audit and retention approval | Security Lead | PV-08 | 4 | 4 | Month 1 | All | Security embedded from discovery | Not Started | Red
D-06 | AI | Enterprise AI platform and model access | AI Platform Owner | PV-01 | 3 | 3 | Start at kickoff | All | Approve model, capacity, logging and data boundaries | Not Started | Amber
D-07 | Operations | Incident Commander and SRE availability for pilot | SRE Leadership | PL-01 | 5 | 5 | Month 2 | Pilot | Pre-book cohort and delegate alternates | Not Started | Amber
D-08 | Data | Representative historical incident benchmark set | SRE / Data Analyst | PV-09 | 4 | 4 | Month 1 | Quality | Sample across services, severities and failure modes | Not Started | Amber
D-09 | Integration | On-call schedules and escalation contacts accessible | On-call Platform Owner | PV-05 | 3 | 3 | Month 1 | Ownership | Validate roster freshness and fallback contacts | Not Started | Amber
D-10 | Change | Deployment and change history correlation data available | Change Management | PR-02 | 8 | 8 | Month 2 | Change Correlation | Standardize timestamps and service identifiers | Not Started | Amber
D-11 | Adoption | Responder training and operating procedure approval | Change Lead | PR-04 | 8 | 8 | Month 2 | Rollout | Role-based training and pilot champions | Not Started | Green
D-12 | Governance | Human-in-the-loop and evidence requirements remain mandatory | SRE / Security | All | All weeks | W1 | Always | All | No production action endpoints; audit recommendations | Not Started | Green

## RAID Register
Top Program Risks
AI quality, security, adoption, integration, operations and governance risks.
ID | Category | Risk | Impact | Linked Tasks | Score | RAG | Mitigation | Contingency | Early Warning | Owner | Due Week | Residual RAG | Status | TPM Notes
R-01 | AI Quality | Incorrect ownership recommendations | Delayed response | PV-05, PL-04 | 16 | Red | Human validation; benchmark testing; confidence scoring | Route to Incident Commander and manual resolver lookup | Accuracy <80% | AI Engineering | 5 | Amber | Open
R-02 | AI Quality | Hallucinated conclusions or unsupported recommendations | Incorrect troubleshooting | PV-07, PV-10 | 16 | Red | Evidence-based outputs; citations; abstain below threshold | Disable affected capability and use standard workflow | Unsupported claim found | AI Engineering / SRE | 5 | Amber | Open
R-03 | Adoption | Low engineer trust and poor usage | Reduced adoption | PL-02, PL-06 | 12 | Amber | Transparency, responder champions, feedback loop | Extend pilot and simplify outputs | Acceptance rate below target | Change Lead | 8 | Amber | Open
R-04 | Security | Sensitive incident data exposed to unauthorized users | Compliance impact | DD-04, PV-08 | 16 | Red | RBAC, read-only access, audit logging and retention controls | Suspend integration and perform security review | Access-control violation | Security Lead | 4 | Amber | Open
R-05 | Knowledge | Incomplete or stale CMDB, runbooks and ownership data | Poor recommendations | PV-03, PV-05 | 15 | Red | Content curation, freshness SLAs and owner attestation | Show uncertainty and route exceptions manually | High no-match rate | Knowledge Manager | 4 | Amber | Open
R-06 | Model Governance | Model drift reduces quality over time | Decreasing accuracy | OP-05 | 12 | Amber | Quarterly review, drift monitoring and retraining | Rollback model/version and recalibrate | Accuracy trend declines | AI Engineering | 14 | Green | Open
R-07 | Integration | API limits or connector outages delay context gathering | Incomplete incident brief | PV-02, PR-02 | 12 | Amber | Caching, retries, health monitoring and graceful degradation | Fallback to manual source access | Connector latency/error spike | Integration Engineering | 4 | Green | Open
R-08 | Operations | AI output distracts responders during Sev-1 incidents | Slower response | PR-06 | 15 | Red | Concise output, confidence thresholds, IC-controlled use | Disable AI panel for active incident | Responder reports noise | SRE Lead | 11 | Amber | Open
R-09 | Measurement | Insufficient incident sample size obscures KPI impact | Unclear value | PL-04, PR-08 | 9 | Amber | Define measurement window and compare matched incidents | Extend measurement period | High metric variance | TPM / Data Analyst | 8 | Green | Open
R-10 | Scope | Pressure to add autonomous remediation | Additional production risk | All | 16 | Red | Enforce non-negotiable scope and architecture controls | Steering Committee scope decision | Action endpoint requested | TPM / Security | 16 | Green | Open

## KPI Scorecard
KPI & Benefits Scorecard
Baselines and targets are from the AI-Assisted Incident Management Program Plan.
Metric | Category | Baseline | Target | Pilot Actual | Production Actual | Target Met? | Data Owner | Measurement Method | Notes
MTTR | Operational | 120 min | 84 min |  |  |  | SRE Lead | Median MTTR for in-scope incidents | 30% reduction target
Ownership Identification | Operational | 20 min | < 5 min |  |  |  | Incident Management | Time from creation to correct resolver ownership | 75% reduction target
Context Gathering | Operational | 30 min | < 3 min |  |  |  | SRE Lead | Time to approved incident brief
Executive Updates | Communication | 15 min | < 2 min |  |  |  | Incident Commander | Time to first approved executive update | AI drafts; human approval
RCA Creation | Post-Incident | 4 hrs | < 30 min |  |  |  | Problem Management | Time to first reviewable RCA draft | Engineering review required
Escalation Accuracy | Quality | 70% | > 90% |  |  |  | Incident Management | Correct resolver recommendation rate
Runbook Utilization | Adoption | 40% | > 80% |  |  |  | Knowledge Manager | Incidents where recommended runbook was used
Recommendation Accuracy | Quality | TBD | >= 80% |  |  |  | SRE / QA | Benchmark and pilot evaluation | Pilot exit criterion
AI Usage Rate | Adoption | TBD | Majority of Sev-1/2 |  |  |  | TPM | Eligible incidents using the agent | Usage alone is not success
Responder Satisfaction | Adoption | TBD | Positive feedback |  |  |  | Change Lead | Post-incident survey