## Executive Dashboard
Executive Dashboard
Program KPI | Target / Count | Month | Apps This Month | Cumulative Apps | Planned Status
Applications in Scope | 20 | M1 | 0 | 0 | Green
Roadmap Records | 107 | M2 | 3 | 3 | Green
Program Duration (Weeks) | 26 | M3 | 5 | 8 | Green
Apps Planned by M5 | 20 | M4 | 6 | 14 | Amber
Availability Target | 99.95% | M5 | 6 | 20 | Amber
RPO Target | <= 5 min | M6 | 0 | 20 | Green
RTO Target | <= 60 min | M6 | 0 | 20 | Green
Legacy Platforms to Retire | 2 | M6 | 0 | 20 | Green
Health Measure | Current
Critical-path records | 43
Tasks Complete | 0
Tasks In Progress | 0
Tasks Blocked | 0
Tasks At Risk | 0
Apps Complete | 0
Apps Ready for Cutover | 0
Dependencies Red | 5
Top Risks Red | 8
Gates Ready | 0

## Executive Roadmap
Legacy to GCP Migration - Executive Roadmap
20 applications ¦ 26 weeks
Month | Weeks | Executive Milestone | Primary Outcomes | Apps This Month | Cumulative Apps | Approval Gate | Gate Owner | Planned Status
M1 | W1-W4 | Foundation Ready | Discovery, dependency map, wave plan, landing zone, security sign-off, replication path | 0 | 0 | GATE-M1 | Security + Platform | Green
M2 | W5-W9 | Pilot Proven | 3 pilot apps, rehearsed rollback, production cutover, hypercare, SLO and DR validation | 3 | 3 | GATE-M2 | Steering Committee | Green
M3 | W10-W13 | Wave 1 Complete | 5 low-complexity apps, DB migration, production cutover, hypercare and DR test | 5 | 8 | GATE-M3 | Steering Committee | Green
M4 | W14-W17 | Wave 2 Complete | 6 complex/shared-DB apps, split cutovers 2a/2b, hypercare and shared-DB DR test | 6 | 14 | GATE-M4 | Steering Committee | Amber
M5 | W18-W21 | Wave 3 Complete | 6 remaining/Tier-1 apps, split cutovers 3a/3b, peak-load test, hypercare and DR test | 6 | 20 | GATE-M5 | Steering Committee | Amber
M6 | W22-W26 | Migration Complete | Portfolio DR, SLO certification, SRE acceptance, archival, compliance and legacy decommission | 0 | 20 | GATE-M6 | Executive Sponsor / SteerCo | Green

## Detailed Monthly Tracker
Detailed Monthly Tracker
Month | Phase | Task ID | Workstream | Task / Milestone | Owner | Type | Start Wk | Duration | End Wk | Planned Start | Planned Finish | Predecessors | Driving Pred. | Link Type | Critical Path | Freeze Check | Status | Deliverable / Evidence | % Complete | TPM Notes / Next Action | RAG | Actual Start | Forecast Finish | Actual Finish | Schedule Variance (Days) | Recovery Plan
M1 | PROGRAM MANAGEMENT & GOVERNANCE | PM-01 | Program Management | Program kickoff, charter, governance and decision rights | TPM | Task | 1 | 1 | 1 | 2026-10-12 | 2026-10-16 |  |  |  | No |  | Not Started | Charter; SteerCo terms of reference | 0% |  | Grey
M1 | PROGRAM MANAGEMENT & GOVERNANCE | PM-02 | Program Management | Stand up RAID log, dependency dashboard and executive dashboard | TPM | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | RAID log (system of record); dashboards live | 0% |  | Grey
M1 | PROGRAM MANAGEMENT & GOVERNANCE | PM-03 | Program Management | Baseline integrated plan, RACI, resource onboarding and SME backfill | TPM | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | Baselined plan; backfill approved | 0% |  | Grey
M1 | PROGRAM MANAGEMENT & GOVERNANCE | PM-04 | Program Management | Agree change calendar: CAB slots, freeze windows, cutover windows | TPM / Change Manager | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | Published change & freeze calendar | 0% |  | Grey
M1 | PROGRAM MANAGEMENT & GOVERNANCE | PM-05 | Program Management | Regulatory and third-party notification plan (cloud outsourcing, vendor risk) | TPM / Compliance | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | PM-01 | PM-01 | FS | No |  | Not Started | Regulatory engagement plan; notification dates | 0% |  | Grey
M1-M6 | PROGRAM MANAGEMENT & GOVERNANCE | PM-06 | Program Management | Weekly SteerCo, Dependency Review Board and RAID review (recurring) | TPM | Task | 2 | 25 | 26 | 2026-10-19 | 2027-04-09 | PM-02 | PM-02 | FS | No |  | Not Started | Weekly status report; decision log | 0% |  | Grey
M1-M6 | PROGRAM MANAGEMENT & GOVERNANCE | PM-07 | Program Management | Monthly executive reporting, budget and cloud-spend vs forecast | TPM / Finance | Task | 4 | 23 | 26 | 2026-11-02 | 2027-04-09 | PM-02 | PM-02 | FS | No |  | Not Started | Monthly exec pack | 0% |  | Grey
M1-M6 | PROGRAM MANAGEMENT & GOVERNANCE | PM-08 | Business Readiness | Business readiness: comms plan, training, runbooks / SOPs (recurring) | Change Manager | Task | 3 | 22 | 24 | 2026-10-26 | 2027-03-26 | PM-03 | PM-03 | FS | No |  | Not Started | Comms calendar; training records; SOPs | 0% |  | Grey
M6 | PROGRAM MANAGEMENT & GOVERNANCE | PM-09 | Program Management | Program closure, final report and lessons learned | TPM | Task | 26 | 1 | 26 | 2027-04-05 | 2027-04-09 | GATE-M6 | GATE-M6 | FS | No |  | Not Started | Closure report; RAID closed | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-01 | Application Migration | Application inventory and CMDB reconciliation (owners, tiers, criticality) | App Teams / TPM | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | Signed-off inventory of 20 apps | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-02 | Application Migration | Technical discovery workshops (runtime, config, secrets, integrations, batch schedules) | Cloud Architects / App SMEs | Task | 1 | 3 | 3 | 2026-10-12 | 2026-10-30 | DS-01 | DS-01 | SS | No |  | Not Started | Per-app discovery pack | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-03 | Program Management | Dependency mapping: shared DBs, APIs, middleware, auth, file transfers, network flows | TPM / Cloud Architects | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-02 | DS-02 | SS | No |  | Not Started | Dependency map; shared-DB groups | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-04 | Database Migration | Database inventory and profiling (size, version, extensions, growth, change rate) | DBA Lead | Task | 1 | 3 | 3 | 2026-10-12 | 2026-10-30 | DS-01 | DS-01 | SS | No |  | Not Started | DB catalogue; compatibility findings | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-05 | Application Migration | 6R disposition and preliminary wave assignment | Cloud Architects / TPM | Task | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | DS-03 | DS-03 | SS | No |  | Not Started | Disposition per app; draft waves | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-06 | Application Migration | .NET Framework containerisation PoC (Windows containers vs rehost) | Cloud Architects / .NET SMEs | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-02 | DS-02 | SS | No |  | Not Started | PoC result; rehost fallback confirmed | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-07 | Platform Foundation | Target architecture decisions (ADRs): compute, PostgreSQL service, DR topology, network | Cloud Architects | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | Signed architecture decision records | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-08 | Cutover & Hypercare | Capture legacy performance baseline; define SLOs / SLIs | SRE Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-02 | DS-02 | SS | No |  | Not Started | Baseline report; SLO definitions | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-09 | Program Management | Wave plan approved (cutover windows, resource loading) | TPM | Task | 4 | 1 | 4 | 2026-11-02 | 2026-11-06 | DS-05 | DS-05 | FS | No |  | Not Started | Approved wave plan | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-10 | Platform Foundation | Migration-factory kit: pipeline templates, cutover playbook, runbook templates | Platform Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-07 | DS-07 | FS | No |  | Not Started | Reusable templates | 0% |  | Grey
M1 | DISCOVERY & PLANNING | DS-11 | Program Management | Cost model and FinOps baseline (dual-run period, egress, commitments) | Finance / TPM | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-07 | DS-07 | FS | No |  | Not Started | Cost forecast; legacy-cost baseline | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-01 | Platform Foundation | Org hierarchy, projects/folders, org policies, billing and budget alerts | Platform Lead | Task | 1 | 2 | 2 | 2026-10-12 | 2026-10-23 | PM-01 | PM-01 | FS | No |  | Not Started | Org structure and policies in IaC | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-02 | Security | Identity & access: SSO federation, groups, least-privilege roles, privileged access | Platform / Security | Task | 1 | 3 | 3 | 2026-10-12 | 2026-10-30 | LZ-01 | LZ-01 | SS | No |  | Not Started | IAM model implemented | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-03 | Platform Foundation | Network: VPC / shared VPC, firewall, DNS, hybrid connectivity (Interconnect + VPN backup) | Platform / Network | Task | 1 | 4 | 4 | 2026-10-12 | 2026-11-06 | PM-01 | PM-01 | FS | Yes |  | Not Started | Tested hybrid connectivity | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-04 | Security | Security controls: CMEK/KMS, secrets management, SIEM logging, vulnerability scanning | Security Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | LZ-01 | LZ-01 | FS | No |  | Not Started | Control baseline deployed | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-05 | Cutover & Hypercare | Observability: monitoring, logging, tracing, alerting, SLO dashboards | SRE / Platform | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | LZ-01 | LZ-01 | FS | No |  | Not Started | Central observability stack | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-06 | Platform Foundation | Compute platform build (per ADR), registry, Windows node pool if required | Platform Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-07 | DS-07 | FS | No |  | Not Started | HA, autoscaling runtime | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-07 | Platform Foundation | CI/CD and IaC: adapt existing pipelines, artifact registry, policy-as-code, deploy templates | Platform Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | LZ-01 | LZ-01 | FS | No |  | Not Started | Reusable pipelines | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-08 | Database Migration | Managed PostgreSQL pattern: HA, automated backup, PITR, cross-region replica, CMEK | DBA Lead | Task | 2 | 3 | 4 | 2026-10-19 | 2026-11-06 | DS-07 | DS-07 | FS | No |  | Not Started | Approved DB reference pattern | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-09 | Database Migration | Data-migration tooling and replication pipeline; throughput test over hybrid link | DBA Lead | Task | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | LZ-08 | LZ-08 | SS | Yes |  | Not Started | Proven replication path | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-10 | Security | Compliance control mapping, evidence capture and landing-zone penetration test | Security Lead | Task | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | LZ-04 | LZ-04 | SS | No |  | Not Started | Control matrix; pen-test report | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | LZ-11 | Security | Landing-zone readiness review and security sign-off | Security + Platform Leads | Task | 4 | 1 | 4 | 2026-11-02 | 2026-11-06 | LZ-10 | LZ-10 | FS | Yes |  | Not Started | Signed review | 0% |  | Grey
M1 | CLOUD FOUNDATION (LANDING ZONE) | GATE-M1 | Program Management | M1: FOUNDATION READY (approver: Security + Platform) | Security + Platform | Gate | 4 | 1 | 4 | 2026-11-02 | 2026-11-06 | LZ-11, DS-09 | LZ-11 | FS | Yes |  | Not Started | Gate approval - nothing deploys to GCP before this | 0% |  | Grey
M2-M6 | CLOUD FOUNDATION (LANDING ZONE) | LZ-12 | Platform Foundation | Platform hardening, quota / capacity checks, cost guardrails (recurring) | Platform Lead | Task | 5 | 21 | 25 | 2026-11-09 | 2027-04-02 | GATE-M1 | GATE-M1 | FS | No |  | Not Started | Capacity ready ahead of each wave | 0% |  | Grey
M1 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-01 | Application Migration | Confirm pilot apps and discovery detail (Tier 3) | App Teams | Task | 3 | 1 | 3 | 2026-10-26 | 2026-10-30 | DS-05 | DS-05 | SS | No |  | Not Started | Pilot scope confirmed | 0% |  | Grey
M1 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-02 | Application Migration | Containerise and build pipelines in CI (no GCP deployment before M1) | App Teams | Task | 3 | 2 | 4 | 2026-10-26 | 2026-11-06 | PL-01 | PL-01 | FS | No |  | Not Started | Container images; pipelines | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-03 | Application Migration | Deploy to GCP non-prod; secrets/config onboarding; observability wiring | Platform / App Teams | Task | 5 | 1 | 5 | 2026-11-09 | 2026-11-13 | GATE-M1, PL-02 | GATE-M1 | FS | Yes |  | Not Started | Pilot running in non-prod | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-04 | Database Migration | Pilot DB initial load and continuous replication; lag monitoring | DBA Lead | Task | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | GATE-M1 | GATE-M1 | FS | No |  | Not Started | Replicating DBs | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-05 | Testing | Functional and regression testing (incl. batch scheduling) | QA Lead | Task | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | PL-03 | PL-03 | FS | No |  | Not Started | Test report | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-06 | Testing | Performance, security (vuln scan, secrets, IAM) and data validation (counts, checksums) | QA / Security / DBA | Task | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | PL-03 | PL-03 | FS | No |  | Not Started | Perf, security and reconciliation reports | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-07 | Cutover & Hypercare | Cutover rehearsal #1 incl. rollback rehearsal | SRE Lead | Task | 6 | 1 | 6 | 2026-11-16 | 2026-11-20 | PL-05 | PL-05 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | GATE-PILOT | Program Management | PILOT GO-LIVE approval (approver: Steering Committee) + CAB | Steering Committee | Gate | 6 | 1 | 6 | 2026-11-16 | 2026-11-20 | PL-07 | PL-07 | FS | Yes |  | Not Started | Go decision logged | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-08 | Cutover & Hypercare | PILOT PRODUCTION CUTOVER (3 apps) | SRE / App Teams | Cutover | 7 | 1 | 7 | 2026-11-23 | 2026-11-27 | GATE-PILOT | GATE-PILOT | FS | Yes | OK | Not Started | Pilot live in GCP | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-09 | Cutover & Hypercare | Pilot hypercare (14+ days, 24x7 SRE support) | SRE / App Teams | Task | 7 | 3 | 9 | 2026-11-23 | 2026-12-11 | PL-08 | PL-08 | FS | Yes |  | Not Started | Incident log; SLO data | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-10 | Cutover & Hypercare | Pilot DR test: zone failure, regional failover, PITR restore (measure RPO / RTO) | SRE / DBA | DR Test | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | PL-08 | PL-08 | FS | Yes | OK | Not Started | DR test report | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | PL-11 | Program Management | Pilot retrospective: update runbooks, tooling and wave estimates | TPM | Task | 9 | 1 | 9 | 2026-12-07 | 2026-12-11 | PL-09 | PL-09 | SS | No |  | Not Started | Lessons learned; updated factory kit | 0% |  | Grey
M2 | PILOT WAVE (3 APPS: 1 .NET, 1 JAVA, 1 BATCH) | GATE-M2 | Program Management | M2: PILOT PROVEN (SLOs, rollback, DR test, runbooks) | Steering Committee | Gate | 9 | 1 | 9 | 2026-12-07 | 2026-12-11 | PL-10, PL-11 | PL-11 | FS | Yes |  | Not Started | Gate to scale to Wave 1-3 | 0% |  | Grey
M1-M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-01 | Application Migration | Containerise, build pipelines and config for 5 Wave 1 apps | App Teams | Task | 3 | 3 | 5 | 2026-10-26 | 2026-11-13 | DS-05 | DS-05 | SS | No |  | Not Started | Images and pipelines | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-02 | Application Migration | Deploy to GCP non-prod; integration endpoints; observability | Platform / App Teams | Task | 5 | 2 | 6 | 2026-11-09 | 2026-11-20 | W1-01, GATE-M1 | W1-01 | FS | No |  | Not Started | Wave 1 in non-prod | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-03 | Database Migration | DB initial load and replication (5 DBs); lag monitoring | DBA Lead | Task | 5 | 3 | 7 | 2026-11-09 | 2026-11-27 | GATE-M1 | GATE-M1 | FS | No |  | Not Started | Replicating DBs | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-04 | Testing | Functional, regression, performance and security testing | QA Lead | Task | 6 | 2 | 7 | 2026-11-16 | 2026-11-27 | W1-02 | W1-02 | FS | No |  | Not Started | Test reports | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-05 | Database Migration | Data validation and reconciliation (counts, checksums) | DBA Lead | Task | 7 | 2 | 8 | 2026-11-23 | 2026-12-04 | W1-03 | W1-03 | FS | No |  | Not Started | Reconciliation sign-off | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-06 | Program Management | Apply pilot lessons learned; finalise runbooks and rollback plan | TPM / SRE | Task | 9 | 1 | 9 | 2026-12-07 | 2026-12-11 | PL-11 | PL-11 | SS | No |  | Not Started | Updated runbooks | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-07 | Cutover & Hypercare | Cutover rehearsal incl. rollback | SRE Lead | Task | 8 | 1 | 8 | 2026-11-30 | 2026-12-04 | W1-04 | W1-04 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M2 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | GATE-W1-GO | Program Management | WAVE 1 GO / NO-GO + CAB approval | CAB | Gate | 9 | 1 | 9 | 2026-12-07 | 2026-12-11 | W1-07, W1-05, W1-06, GATE-M2 | W1-07 | FS | Yes |  | Not Started | Approved change request | 0% |  | Grey
M3 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-08 | Cutover & Hypercare | WAVE 1 PRODUCTION CUTOVER (5 apps) - before year-end freeze | SRE / App Teams | Cutover | 10 | 1 | 10 | 2026-12-14 | 2026-12-18 | GATE-W1-GO, GATE-M2 | GATE-W1-GO | FS | Yes | OK | Not Started | Wave 1 live in GCP | 0% |  | Grey
M3 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-09 | Cutover & Hypercare | Wave 1 hypercare (runs through the freeze - no changes) | SRE / App Teams | Task | 11 | 3 | 13 | 2026-12-21 | 2027-01-08 | W1-08 | W1-08 | FS | Yes |  | Not Started | Hypercare exit evidence | 0% |  | Grey
M3 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-10 | Cutover & Hypercare | Wave 1 DR test (zone and regional failover) | SRE / DBA | DR Test | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | W1-09 | W1-09 | FS | Yes | OK | Not Started | DR test report | 0% |  | Grey
M3 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-11 | Cutover & Hypercare | Wave 1 performance validation and wave closure (Sev-1/2 closed) | TPM / SRE | Task | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | W1-09 | W1-09 | FS | No |  | Not Started | Closure checklist | 0% |  | Grey
M3 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | GATE-M3 | Program Management | M3: WAVE 1 COMPLETE | Steering Committee (proposed) | Gate | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | W1-10, W1-11 | W1-11 | FS | Yes |  | Not Started | Gate approval | 0% |  | Grey
M4 | WAVE 1 (5 APPS - LOW COMPLEXITY, INDEPENDENT) | W1-12 | Platform Foundation | Wave 1 legacy shutdown (read-only retention) | Platform / App Teams | Task | 14 | 2 | 15 | 2027-01-11 | 2027-01-22 | GATE-M3 | GATE-M3 | FS | No |  | Not Started | Legacy workloads stopped | 0% |  | Grey
M2 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-01 | Application Migration | Deep-dive: shared-DB groups (SDB-A/B/C), integration contracts, cutover grouping | Cloud Architects / DBA | Task | 5 | 3 | 7 | 2026-11-09 | 2026-11-27 | DS-09 | DS-09 | FS | No |  | Not Started | Cutover grouping approved | 0% |  | Grey
M2 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-02 | Application Migration | Containerise / limited refactor of 4 apps (2 Refactor, 2 Replatform) | App Teams | Task | 6 | 4 | 9 | 2026-11-16 | 2026-12-11 | W2-01 | W2-01 | SS | No |  | Not Started | Images and pipelines | 0% |  | Grey
M2 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-03 | Application Migration | Rehost 2 legacy .NET apps to GCE Windows VMs | App Teams / Platform | Task | 7 | 3 | 9 | 2026-11-23 | 2026-12-11 | W2-01 | W2-01 | FS | No |  | Not Started | Rehosted apps in non-prod | 0% |  | Grey
M2-M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-04 | Application Migration | Deploy to non-prod and integration environments (shared-DB test) | Platform Lead | Task | 9 | 2 | 10 | 2026-12-07 | 2026-12-18 | W2-02 | W2-02 | FS | No |  | Not Started | Integrated test environment | 0% |  | Grey
M2-M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-05 | Database Migration | Shared-DB replication and initial load (largest DBs); throughput and lag monitoring | DBA Lead | Task | 9 | 5 | 13 | 2026-12-07 | 2027-01-08 | GATE-M2 | GATE-M2 | FS | Yes |  | Not Started | Replicating shared DBs | 0% |  | Grey
M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-06 | Testing | Functional, integration, performance and security testing | QA Lead | Task | 10 | 3 | 12 | 2026-12-14 | 2027-01-01 | W2-04 | W2-04 | FS | No |  | Not Started | Test reports | 0% |  | Grey
M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-07 | Database Migration | Data validation and reconciliation | DBA Lead | Task | 11 | 3 | 13 | 2026-12-21 | 2027-01-08 | W2-05 | W2-05 | SS | No |  | Not Started | Reconciliation sign-off | 0% |  | Grey
M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-08 | Cutover & Hypercare | Cutover rehearsal #1 | SRE Lead | Task | 12 | 1 | 12 | 2026-12-28 | 2027-01-01 | W2-06 | W2-06 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-09 | Cutover & Hypercare | Cutover rehearsal #2 (full simulation + reverse-replication rollback) | SRE Lead | Task | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | W2-08 | W2-08 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M3 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | GATE-W2-GO | Program Management | WAVE 2 GO / NO-GO + CAB approval | CAB | Gate | 13 | 1 | 13 | 2027-01-04 | 2027-01-08 | W2-09, W2-07 | W2-09 | FS | Yes |  | Not Started | Approved change request | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-10 | Cutover & Hypercare | CUTOVER 2a: shared-DB groups SDB-A and SDB-B (4 Tier-2 apps) | SRE / App Teams / DBA | Cutover | 14 | 1 | 14 | 2027-01-11 | 2027-01-15 | GATE-W2-GO | GATE-W2-GO | FS | Yes | OK | Not Started | 4 apps live | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-11 | Cutover & Hypercare | CUTOVER 2b: shared-DB group SDB-C (2 Tier-1 apps) | SRE / App Teams / DBA | Cutover | 15 | 1 | 15 | 2027-01-18 | 2027-01-22 | W2-10 | W2-10 | FS | Yes | OK | Not Started | 2 apps live | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-12 | Cutover & Hypercare | Wave 2 hypercare | SRE / App Teams | Task | 15 | 3 | 17 | 2027-01-18 | 2027-02-05 | W2-10 | W2-10 | FS | Yes |  | Not Started | Hypercare exit evidence | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-13 | Cutover & Hypercare | Wave 2 DR test (shared-DB failover; RPO / RTO) | SRE / DBA | DR Test | 16 | 1 | 16 | 2027-01-25 | 2027-01-29 | W2-11 | W2-11 | FS | Yes | OK | Not Started | DR test report | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-14 | Cutover & Hypercare | Wave 2 performance validation and wave closure | TPM / SRE | Task | 17 | 1 | 17 | 2027-02-01 | 2027-02-05 | W2-12 | W2-12 | FS | No |  | Not Started | Closure checklist | 0% |  | Grey
M4 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | GATE-M4 | Program Management | M4: WAVE 2 COMPLETE | Steering Committee (proposed) | Gate | 17 | 1 | 17 | 2027-02-01 | 2027-02-05 | W2-14, W2-13 | W2-14 | FS | Yes |  | Not Started | Gate approval | 0% |  | Grey
M5 | WAVE 2 (6 APPS - COMPLEX, SHARED DATABASES, LEGACY WORKLOADS) | W2-15 | Platform Foundation | Wave 2 legacy shutdown (read-only retention) | Platform / App Teams | Task | 18 | 3 | 20 | 2027-02-08 | 2027-02-26 | GATE-M4 | GATE-M4 | FS | No |  | Not Started | Legacy workloads stopped | 0% |  | Grey
M2 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-01 | Application Migration | Detailed discovery incl. Tier-1 resiliency, vendor and regulatory touchpoints | Cloud Architects | Task | 7 | 3 | 9 | 2026-11-23 | 2026-12-11 | DS-09 | DS-09 | FS | No |  | Not Started | Tier-1 design addendum | 0% |  | Grey
M2-M3 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-02 | Application Migration | Containerise / refactor / build pipelines (5 Replatform, 1 Refactor) | App Teams | Task | 9 | 5 | 13 | 2026-12-07 | 2027-01-08 | W3-01 | W3-01 | FS | No |  | Not Started | Images and pipelines | 0% |  | Grey
M3-M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-03 | Application Migration | Deploy to non-prod and integration environments | Platform Lead | Task | 13 | 2 | 14 | 2027-01-04 | 2027-01-15 | W3-02 | W3-02 | FS | No |  | Not Started | Wave 3 in non-prod | 0% |  | Grey
M3-M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-04 | Database Migration | DB initial load and replication for Tier-1/2 DBs (largest data volume) | DBA Lead | Task | 12 | 6 | 17 | 2026-12-28 | 2027-02-05 | GATE-M2 | GATE-M2 | FS | Yes |  | Not Started | Replicating DBs | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-05 | Testing | Functional, integration, performance and security testing | QA Lead | Task | 14 | 3 | 16 | 2027-01-11 | 2027-01-29 | W3-03 | W3-03 | FS | No |  | Not Started | Test reports | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-06 | Testing | Tier-1 peak-load and resiliency testing at production scale | QA / SRE | Task | 15 | 2 | 16 | 2027-01-18 | 2027-01-29 | W3-05 | W3-05 | SS | Yes |  | Not Started | Load and resiliency report | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-07 | Database Migration | Data validation and reconciliation | DBA Lead | Task | 15 | 3 | 17 | 2027-01-18 | 2027-02-05 | W3-04 | W3-04 | SS | No |  | Not Started | Reconciliation sign-off | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-08 | Cutover & Hypercare | Cutover rehearsal #1 | SRE Lead | Task | 16 | 1 | 16 | 2027-01-25 | 2027-01-29 | W3-05 | W3-05 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-09 | Cutover & Hypercare | Cutover rehearsal #2 (full simulation incl. rollback, Tier 1) | SRE Lead | Task | 17 | 1 | 17 | 2027-02-01 | 2027-02-05 | W3-08 | W3-08 | FS | Yes |  | Not Started | Rehearsal record | 0% |  | Grey
M4 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | GATE-W3-GO | Program Management | WAVE 3 GO / NO-GO + CAB approval | CAB | Gate | 17 | 1 | 17 | 2027-02-01 | 2027-02-05 | W3-09, W3-07 | W3-09 | FS | Yes |  | Not Started | Approved change request | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-10 | Cutover & Hypercare | CUTOVER 3a: Tier-2 apps (3 apps) | SRE / App Teams / DBA | Cutover | 18 | 1 | 18 | 2027-02-08 | 2027-02-12 | GATE-W3-GO | GATE-W3-GO | FS | Yes | OK | Not Started | 3 apps live | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-11 | Cutover & Hypercare | CUTOVER 3b: Tier-1 apps (3 apps) - final production cutover | SRE / App Teams / DBA | Cutover | 19 | 1 | 19 | 2027-02-15 | 2027-02-19 | W3-10 | W3-10 | FS | Yes | OK | Not Started | 3 Tier-1 apps live | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-12 | Cutover & Hypercare | Wave 3 hypercare (Tier-1 exit may need extension - see R-11) | SRE / App Teams | Task | 19 | 3 | 21 | 2027-02-15 | 2027-03-05 | W3-10 | W3-10 | FS | Yes |  | Not Started | Hypercare exit evidence | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-13 | Cutover & Hypercare | Wave 3 DR test (Tier-1 regional failover; RPO / RTO) | SRE / DBA | DR Test | 20 | 1 | 20 | 2027-02-22 | 2027-02-26 | W3-11 | W3-11 | FS | Yes | OK | Not Started | DR test report | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-14 | Cutover & Hypercare | Wave 3 performance validation and wave closure | TPM / SRE | Task | 21 | 1 | 21 | 2027-03-01 | 2027-03-05 | W3-12 | W3-12 | FS | No |  | Not Started | Closure checklist | 0% |  | Grey
M5 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | GATE-M5 | Program Management | M5: WAVE 3 COMPLETE | Steering Committee (proposed) | Gate | 21 | 1 | 21 | 2027-03-01 | 2027-03-05 | W3-14, W3-13 | W3-14 | FS | Yes |  | Not Started | Gate approval | 0% |  | Grey
M6 | WAVE 3 (6 APPS - REMAINING APPS, INCL. TIER 1, FINAL CUTOVERS) | W3-15 | Platform Foundation | Wave 3 legacy shutdown (read-only retention) | Platform / App Teams | Task | 22 | 2 | 23 | 2027-03-08 | 2027-03-19 | GATE-M5 | GATE-M5 | FS | No |  | Not Started | Legacy workloads stopped | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-01 | Cutover & Hypercare | Full-portfolio DR exercise: regional failover and failback, measured RPO / RTO (20 apps) | SRE / DBA | DR Test | 22 | 2 | 23 | 2027-03-08 | 2027-03-19 | GATE-M5 | GATE-M5 | FS | Yes | OK | Not Started | Portfolio DR report | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-02 | Cutover & Hypercare | Portfolio SLO / availability validation report (99.95% target) | SRE Lead | Task | 22 | 3 | 24 | 2027-03-08 | 2027-03-26 | GATE-M5 | GATE-M5 | FS | No |  | Not Started | SLO attainment report | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-03 | Cutover & Hypercare | Hypercare exit certification, all waves (Sev-1 14d, Sev-2 7d, defects, runbooks) | TPM / SRE | Task | 22 | 1 | 22 | 2027-03-08 | 2027-03-12 | W3-14 | W3-14 | FS | No |  | Not Started | Hypercare exit certificate | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-04 | Cutover & Hypercare | SRE handoff: runbook validation, on-call readiness, support model, incident process | SRE Lead | Task | 22 | 4 | 25 | 2027-03-08 | 2027-04-02 | GATE-M5 | GATE-M5 | FS | No |  | Not Started | Validated runbooks; on-call live | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-05 | Database Migration | Legacy data archival and retention validated; final backups taken | DBA / Compliance | Task | 22 | 3 | 24 | 2027-03-08 | 2027-03-26 | GATE-M5 | GATE-M5 | FS | No |  | Not Started | Archive and retention evidence | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | GATE-DR | Program Management | DR VALIDATION sign-off (approver: Infrastructure Leadership) | Infrastructure Leadership | Gate | 24 | 1 | 24 | 2027-03-22 | 2027-03-26 | FN-01 | FN-01 | FS | Yes |  | Not Started | DR validated | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-06 | Platform Foundation | Decommission readiness review (zero traffic, no consumers, contract / lease notices) | Platform / TPM | Task | 23 | 1 | 23 | 2027-03-15 | 2027-03-19 | FN-05 | FN-05 | SS | Yes |  | Not Started | Readiness checklist | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-07 | Program Management | FinOps review: rightsizing, commitments, cost vs forecast | Finance / Platform | Task | 23 | 3 | 25 | 2027-03-15 | 2027-04-02 | GATE-M5 | GATE-M5 | FS | No |  | Not Started | FinOps report | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-08 | Security | Final compliance evidence pack and audit sign-off | Security Lead | Task | 24 | 2 | 25 | 2027-03-22 | 2027-04-02 | FN-01 | FN-01 | FS | No |  | Not Started | Evidence pack accepted | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | GATE-DECOM | Program Management | LEGACY DECOMMISSION approval (approver: Executive Sponsor) | Executive Sponsor | Gate | 24 | 1 | 24 | 2027-03-22 | 2027-03-26 | FN-06, GATE-DR | FN-06 | FS | Yes |  | Not Started | Decommission authorised | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-09 | Platform Foundation | Decommission legacy infrastructure (Platforms A and B), secure wipe, contract exit | Platform Lead | Task | 25 | 2 | 26 | 2027-03-29 | 2027-04-09 | GATE-DECOM | GATE-DECOM | FS | Yes |  | Not Started | Legacy retired | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | FN-10 | Cutover & Hypercare | SRE formal acceptance of ownership | SRE Lead | Task | 25 | 1 | 25 | 2027-03-29 | 2027-04-02 | FN-04 | FN-04 | FS | Yes |  | Not Started | Signed acceptance | 0% |  | Grey
M6 | DR VALIDATION, DECOMMISSION & SRE HANDOFF | GATE-M6 | Program Management | M6: MIGRATION COMPLETE | Executive Sponsor / SteerCo | Gate | 26 | 1 | 26 | 2027-04-05 | 2027-04-09 | FN-09, FN-10, FN-02 | FN-09 | FS | Yes |  | Not Started | Program exit | 0% |  | Grey

## Application Tracker
Application Migration Tracker
App ID | Application | Runtime | Workload Type | Tier | Wave | Disposition | Source Platform | DB Size (TB) | Shared DB Group | Cutover Window | Cutover Week | Cutover Date | Key Dependencies / Notes | Current Status
App-01 | App-01 [rename] | .NET | Web | 3 | Pilot | Replatform | Legacy A | 0.5 |  | Pilot | 7 | 2026-11-23 | Pilot .NET app; validates Windows-container path and IIS/auth handling | Not Started
App-02 | App-02 [rename] | Java | API | 3 | Pilot | Replatform | Legacy B | 0.8 |  | Pilot | 7 | 2026-11-23 | Pilot Java app; validates JVM container baseline and DB replication | Not Started
App-03 | App-03 [rename] | Java | Batch | 3 | Pilot | Replatform | Legacy A | 0.4 |  | Pilot | 7 | 2026-11-23 | Pilot batch app; validates scheduler integration and job re-runs | Not Started
App-04 | App-04 [rename] | .NET | Web | 3 | Wave 1 | Replatform | Legacy B | 1 |  | W1 | 10 | 2026-12-14 | Independent; internal users | Not Started
App-05 | App-05 [rename] | .NET | API | 2 | Wave 1 | Replatform | Legacy A | 1.5 |  | W1 | 10 | 2026-12-14 | Independent API; confirm consumer list in discovery | Not Started
App-06 | App-06 [rename] | Java | API | 3 | Wave 1 | Replatform | Legacy B | 0.8 |  | W1 | 10 | 2026-12-14 | Independent service | Not Started
App-07 | App-07 [rename] | Java | Web | 3 | Wave 1 | Replatform | Legacy A | 0.6 |  | W1 | 10 | 2026-12-14 | Independent; SSO integration | Not Started
App-08 | App-08 [rename] | Java | Batch | 3 | Wave 1 | Replatform | Legacy B | 0.9 |  | W1 | 10 | 2026-12-14 | Batch; scheduler / file-drop dependencies | Not Started
App-09 | App-09 [rename] | .NET | Web | 2 | Wave 2 | Rehost | Legacy A | 4 | SDB-A | W2a | 14 | 2027-01-11 | Legacy .NET Framework; shares DB with App-10; GCE Windows VM | Not Started
App-10 | App-10 [rename] | .NET | API | 2 | Wave 2 | Rehost | Legacy A | 0 | SDB-A | W2a | 14 | 2027-01-11 | Shares SDB-A with App-09 - must cut over together | Not Started
App-11 | App-11 [rename] | Java | Web | 2 | Wave 2 | Refactor | Legacy B | 3.5 | SDB-B | W2a | 14 | 2027-01-11 | Shares DB with App-12; limited refactor to decouple | Not Started
App-12 | App-12 [rename] | Java | API | 2 | Wave 2 | Replatform | Legacy B | 0 | SDB-B | W2a | 14 | 2027-01-11 | Shares SDB-B with App-11 | Not Started
App-13 | App-13 [rename] | .NET | Web | 1 | Wave 2 | Refactor | Legacy A | 6 | SDB-C | W2b | 15 | 2027-01-18 | Revenue-critical; shares DB with App-14; strict RTO / RPO | Not Started
App-14 | App-14 [rename] | .NET | API | 1 | Wave 2 | Replatform | Legacy B | 0 | SDB-C | W2b | 15 | 2027-01-18 | Shares SDB-C with App-13; customer-facing | Not Started
App-15 | App-15 [rename] | Java | API | 2 | Wave 3 | Replatform | Legacy A | 2.5 |  | W3a | 18 | 2027-02-08 | Depends on Wave 2 services - validate in coexistence | Not Started
App-16 | App-16 [rename] | .NET | Web | 2 | Wave 3 | Replatform | Legacy B | 3 |  | W3a | 18 | 2027-02-08 | Business-critical; third-party integrations | Not Started
App-17 | App-17 [rename] | Java | Batch | 2 | Wave 3 | Replatform | Legacy A | 1.5 |  | W3a | 18 | 2027-02-08 | Batch; month-end processing - avoid month-end cutover | Not Started
App-18 | App-18 [rename] | .NET | Web | 1 | Wave 3 | Replatform | Legacy B | 7.5 |  | W3b | 19 | 2027-02-15 | Tier 1; largest DB; peak-load testing mandatory | Not Started
App-19 | App-19 [rename] | Java | API | 1 | Wave 3 | Refactor | Legacy A | 4 |  | W3b | 19 | 2027-02-15 | Tier 1; refactor for HA; partner traffic | Not Started
App-20 | App-20 [rename] | .NET | Web | 1 | Wave 3 | Replatform | Legacy B | 5 |  | W3b | 19 | 2027-02-15 | Tier 1; customer-facing; vendor IP allow-listing | Not Started

## Gate Readiness
Milestone & Gate Readiness
Gate ID | Gate / Decision Point | Target Week | Target Date | Approver | # Criteria | # Complete | Readiness % | RAG | Decision / Notes
GATE-M1 | M1: FOUNDATION READY | 4 | 2026-11-02 | Security + Platform | 10 | 0 | 0% | Not Started
GATE-PILOT | PILOT GO-LIVE APPROVAL + CAB | 6 | 2026-11-20 | Steering Committee / CAB | 6 | 0 | 0% | Not Started
GATE-M2 | M2: PILOT PROVEN | 9 | 2026-12-11 | Steering Committee | 8 | 0 | 0% | Not Started
GATE-W1-GO | WAVE 1 GO / NO-GO + CAB | 9 | 2026-12-11 | CAB | 8 | 0 | 0% | Not Started
GATE-M3 | M3: WAVE 1 COMPLETE | 13 | 2027-01-08 | Steering Committee | 7 | 0 | 0% | Not Started
GATE-W2-GO | WAVE 2 GO / NO-GO + CAB | 13 | 2027-01-08 | CAB | 8 | 0 | 0% | Not Started
GATE-M4 | M4: WAVE 2 COMPLETE | 17 | 2027-02-05 | Steering Committee | 7 | 0 | 0% | Not Started
GATE-W3-GO | WAVE 3 GO / NO-GO + CAB | 17 | 2027-02-05 | CAB | 8 | 0 | 0% | Not Started
GATE-M5 | M5: WAVE 3 COMPLETE | 21 | 2027-03-05 | Steering Committee | 7 | 0 | 0% | Not Started
GATE-DR | DR VALIDATION SIGN-OFF | 24 | 2027-03-26 | Infrastructure Leadership | 6 | 0 | 0% | Not Started
GATE-DECOM | LEGACY DECOMMISSION APPROVAL | 24 | 2027-03-26 | Executive Sponsor | 6 | 0 | 0% | Not Started
GATE-M6 | M6: MIGRATION COMPLETE | 26 | 2027-04-09 | Executive Sponsor / SteerCo | 7 | 0 | 0% | Not Started
RAG Logic
Not Started | 0 criteria complete
Red | 1%-74% complete
Amber | 75%-99% complete
Green | 100% complete

## Gate Criteria Checklist
Gate Exit-Criteria Checklist
Update only the Status column. Gate Readiness calculates automatically from this checklist.
Gate ID | Exit Criterion | Owner | Evidence / Artefact | Source | Status | Comments / Evidence Link
GATE-M1 | Landing zone approved | Platform Lead | Architecture review record | Plan | Not Started
GATE-M1 | Security sign-off obtained | Security Lead | Signed assessment; pen-test closure | Plan | Not Started
GATE-M1 | Application inventory completed | TPM | Inventory reconciled with CMDB (20 apps) | Plan | Not Started
GATE-M1 | Dependency map completed | TPM | Dependency map; shared-DB groups | Plan | Not Started
GATE-M1 | Wave plan approved | TPM | Wave plan signed by SteerCo | Plan | Not Started
GATE-M1 | Hybrid connectivity tested at required bandwidth | Platform Lead | Throughput test report | Added | Not Started
GATE-M1 | Target architecture decisions approved (compute, PostgreSQL service, DR topology) | Cloud Architects | Signed ADRs | Added | Not Started
GATE-M1 | Change calendar, freeze windows and CAB slots agreed | Change Manager | Published calendar | Added | Not Started
GATE-M1 | Compliance control mapping and evidence process accepted | Security Lead | Control matrix | Added | Not Started
GATE-M1 | Managed PostgreSQL HA / PITR / cross-region replica pattern proven in sandbox | DBA Lead | Test record | Added | Not Started
GATE-PILOT | Functional, regression, performance and security tests complete | QA Lead | Test summary report | Plan | Not Started
GATE-PILOT | Data validation: counts and checksums reconcile 100% | DBA Lead | Reconciliation report | Plan | Not Started
GATE-PILOT | Rollback validated in rehearsal | SRE Lead | Rehearsal record | Plan | Not Started
GATE-PILOT | CAB change approval | Change Manager | Approved change request | Plan | Not Started
GATE-PILOT | Stakeholder sign-off | Application Owners | Sign-off record | Plan | Not Started
GATE-PILOT | War-room roster, comms plan and decision log ready | TPM | Cutover comms pack | Added | Not Started
GATE-M2 | Pilot applications successfully migrated | TPM | Cutover record | Plan | Not Started
GATE-M2 | SLOs validated | SRE Lead | SLO report | Plan | Not Started
GATE-M2 | Migration runbooks completed | SRE Lead | Validated runbooks | Plan | Not Started
GATE-M2 | Rollback tested | SRE Lead | Rehearsal record | Plan | Not Started
GATE-M2 | DR test passed | SRE Lead / DBA Lead | DR test report | Plan | Not Started
GATE-M2 | 14 days Sev-1-free hypercare and no open Sev-2 | SRE Lead | Incident log | Added | Not Started
GATE-M2 | Lessons learned incorporated into factory kit and wave estimates | TPM | Retro actions closed | Added | Not Started
GATE-M2 | Cloud cost actuals reviewed against forecast | Finance | Cost report | Added | Not Started
GATE-W1-GO | Test completion (functional, performance, security) | QA Lead | Test summary report | Plan | Not Started
GATE-W1-GO | Rollback validated in rehearsal | SRE Lead | Rehearsal record | Plan | Not Started
GATE-W1-GO | Change approval (CAB) | Change Manager | Approved change request | Plan | Not Started
GATE-W1-GO | Stakeholder sign-off | Application Owners | Sign-off record | Plan | Not Started
GATE-W1-GO | Replication lag within threshold; data reconciled | DBA Lead | Reconciliation report | Added | Not Started
GATE-W1-GO | No open Sev-1 / Sev-2 from previous wave | SRE Lead | Incident log | Added | Not Started
GATE-W1-GO | Vendor allow-listing, DNS and certificate changes ready | Platform Lead | Checklist | Added | Not Started
GATE-W1-GO | Freeze-calendar check passed (Roadmap Freeze Check = OK) | TPM | Roadmap | Added | Not Started
GATE-M3 | Applications migrated | TPM | Cutover record | Plan | Not Started
GATE-M3 | Performance validated | SRE Lead | Perf report | Plan | Not Started
GATE-M3 | No unresolved Sev-1 or Sev-2 issues | SRE Lead | Incident log | Plan | Not Started
GATE-M3 | Hypercare completed (14-day Sev-1-free) | SRE Lead | Hypercare exit evidence | Plan | Not Started
GATE-M3 | Wave DR test passed (RPO <= 5 min, RTO <= 60 min) | SRE Lead / DBA Lead | DR test report | Added | Not Started
GATE-M3 | Legacy apps set read-only; shutdown scheduled | Platform Lead | Change record | Added | Not Started
GATE-M3 | Lessons learned captured and applied | TPM | Retro actions | Added | Not Started
GATE-W2-GO | Test completion (functional, performance, security) | QA Lead | Test summary report | Plan | Not Started
GATE-W2-GO | Rollback validated in rehearsal | SRE Lead | Rehearsal record | Plan | Not Started
GATE-W2-GO | Change approval (CAB) | Change Manager | Approved change request | Plan | Not Started
GATE-W2-GO | Stakeholder sign-off | Application Owners | Sign-off record | Plan | Not Started
GATE-W2-GO | Replication lag within threshold; data reconciled | DBA Lead | Reconciliation report | Added | Not Started
GATE-W2-GO | No open Sev-1 / Sev-2 from previous wave | SRE Lead | Incident log | Added | Not Started
GATE-W2-GO | Vendor allow-listing, DNS and certificate changes ready | Platform Lead | Checklist | Added | Not Started
GATE-W2-GO | Freeze-calendar check passed (Roadmap Freeze Check = OK) | TPM | Roadmap | Added | Not Started
GATE-M4 | Applications migrated | TPM | Cutover record | Plan | Not Started
GATE-M4 | Performance validated | SRE Lead | Perf report | Plan | Not Started
GATE-M4 | No unresolved Sev-1 or Sev-2 issues | SRE Lead | Incident log | Plan | Not Started
GATE-M4 | Hypercare completed (14-day Sev-1-free) | SRE Lead | Hypercare exit evidence | Plan | Not Started
GATE-M4 | Wave DR test passed (RPO <= 5 min, RTO <= 60 min) | SRE Lead / DBA Lead | DR test report | Added | Not Started
GATE-M4 | Legacy apps set read-only; shutdown scheduled | Platform Lead | Change record | Added | Not Started
GATE-M4 | Lessons learned captured and applied | TPM | Retro actions | Added | Not Started
GATE-W3-GO | Test completion (functional, performance, security) | QA Lead | Test summary report | Plan | Not Started
GATE-W3-GO | Rollback validated in rehearsal | SRE Lead | Rehearsal record | Plan | Not Started
GATE-W3-GO | Change approval (CAB) | Change Manager | Approved change request | Plan | Not Started
GATE-W3-GO | Stakeholder sign-off | Application Owners | Sign-off record | Plan | Not Started
GATE-W3-GO | Replication lag within threshold; data reconciled | DBA Lead | Reconciliation report | Added | Not Started
GATE-W3-GO | No open Sev-1 / Sev-2 from previous wave | SRE Lead | Incident log | Added | Not Started
GATE-W3-GO | Vendor allow-listing, DNS and certificate changes ready | Platform Lead | Checklist | Added | Not Started
GATE-W3-GO | Freeze-calendar check passed (Roadmap Freeze Check = OK) | TPM | Roadmap | Added | Not Started
GATE-M5 | Applications migrated | TPM | Cutover record | Plan | Not Started
GATE-M5 | Performance validated | SRE Lead | Perf report | Plan | Not Started
GATE-M5 | No unresolved Sev-1 or Sev-2 issues | SRE Lead | Incident log | Plan | Not Started
GATE-M5 | Hypercare completed (14-day Sev-1-free) | SRE Lead | Hypercare exit evidence | Plan | Not Started
GATE-M5 | Wave DR test passed (RPO <= 5 min, RTO <= 60 min) | SRE Lead / DBA Lead | DR test report | Added | Not Started
GATE-M5 | Legacy apps set read-only; shutdown scheduled | Platform Lead | Change record | Added | Not Started
GATE-M5 | Lessons learned captured and applied | TPM | Retro actions | Added | Not Started
GATE-DR | Zone-failure test passed | SRE Lead | DR test report | Plan | Not Started
GATE-DR | Regional failover test passed | SRE Lead | DR test report | Plan | Not Started
GATE-DR | Measured RPO <= 5 minutes | DBA Lead | Measured results | Plan | Not Started
GATE-DR | Measured RTO <= 60 minutes | SRE Lead | Measured results | Plan | Not Started
GATE-DR | Failback validated | SRE Lead | DR test report | Added | Not Started
GATE-DR | Infrastructure Leadership sign-off | Infrastructure Leadership | Sign-off record | Plan | Not Started
GATE-DECOM | All applications live in GCP; hypercare exited | TPM | Hypercare certificate | Plan | Not Started
GATE-DECOM | Legacy data archived; retention requirements validated | DBA Lead / Compliance | Archive evidence | Added | Not Started
GATE-DECOM | Zero traffic to legacy confirmed | Platform Lead | Traffic reports | Added | Not Started
GATE-DECOM | Contract / lease exit notices issued | Procurement | Notices | Added | Not Started
GATE-DECOM | Rollback window closed (point of no return agreed) | TPM | Decision log | Added | Not Started
GATE-DECOM | Executive Sponsor approval | Executive Sponsor | Sign-off record | Plan | Not Started
GATE-M6 | All 20 applications running in GCP | TPM | Inventory vs status | Plan | Not Started
GATE-M6 | DR validated | SRE Lead | Portfolio DR report | Plan | Not Started
GATE-M6 | SLOs green | SRE Lead | SLO report | Plan | Not Started
GATE-M6 | Legacy infrastructure decommissioned | Platform Lead | Decommission evidence | Plan | Not Started
GATE-M6 | SRE handoff completed | SRE Lead | Signed acceptance | Plan | Not Started
GATE-M6 | Final compliance evidence pack accepted | Security Lead | Evidence pack | Added | Not Started
GATE-M6 | Budget variance reported and closed | Finance | Final cost report | Added | Not Started

## Critical Dependencies
Dependency Register
ID | Category | Dependency | Provider / Owner | Blocks Task ID | Blocked Task | Needed-by Wk | Needed-by Date | Lead Time (wks) | Latest Start Wk | Latest Start Date | Urgency | Waves Affected | Mitigation / Action | Status | RAG
D-01 | Technical | Hybrid connectivity (Dedicated/Partner Interconnect + HA VPN backup) sized for tens-of-TB replication; carrier circuit and cross-connect provisioning | Platform Lead / Network / Carrier | LZ-09 | Data-migration tooling and replication pipeline; throughput test over hybrid link | 3 | 2026-10-26 | 6 | -3 | 2026-09-14 | START AT KICKOFF | All | Order circuits at kickoff; stand up HA VPN as interim path; size for peak concurrent replication (Wave 2 + 3); fallback: offline transfer appliance for initial seed | Not Started | Red
D-02 | Technical | Identity: SSO / IdP federation, service accounts, Kerberos / Windows-integrated auth for .NET apps across GCP and legacy | Identity team / Security | PL-03 | Deploy to GCP non-prod; secrets/config onboarding; observability wiring | 5 | 2026-11-09 | 3 | 2 | 2026-10-19 | START IN MONTH 1 | All (.NET esp.) | Design in DS-07; test in pilot .NET app; keep AD trust path during coexistence | Not Started | Amber
D-03 | Technical | Shared databases between apps (SDB-A / B / C) - apps must cut over together or be decoupled first | DBA Lead / App Teams | W2-05 | Shared-DB replication and initial load (largest DBs); throughput and lag monitoring | 9 | 2026-12-07 | 5 | 4 | 2026-11-02 | START IN MONTH 1 | Wave 2 | Group apps by DB for cutover; decouple via APIs where cheap; rehearse group cutover twice | Not Started | Red
D-04 | Technical | Middleware / message queues reachable from GCP while apps are split across platforms | Middleware team | W2-04 | Deploy to non-prod and integration environments (shared-DB test) | 9 | 2026-12-07 | 4 | 5 | 2026-11-09 |  | Waves 1-3 | Network path + firewall rules before non-prod; confirm MQ licensing / cloud support | Not Started | Amber
D-05 | Technical | File transfers (SFTP / MFT) - partner endpoints, keys and schedules must be re-pointed | Integration team / App Teams | W2-10 | CUTOVER 2a: shared-DB groups SDB-A and SDB-B (4 Tier-2 apps) | 14 | 2027-01-11 | 6 | 8 | 2026-11-30 |  | Waves 1-3 | Inventory all inbound/outbound transfers in DS-03; agree partner change windows early | Not Started | Amber
D-06 | Technical | Internal API coexistence - chatty calls between GCP and legacy add latency during split state | Cloud Architects | W2-04 | Deploy to non-prod and integration environments (shared-DB test) | 9 | 2026-12-07 | 3 | 6 | 2026-11-16 |  | Waves 2-3 | Keep chatty apps in the same wave; measure latency in non-prod; use caching / batching where needed | Not Started | Amber
D-07 | Technical | DNS, load-balancer and certificate (PKI) cutover; lower TTLs 48-72h before each cutover | Network / Platform | W1-08 | WAVE 1 PRODUCTION CUTOVER (5 apps) - before year-end freeze | 10 | 2026-12-14 | 3 | 7 | 2026-11-23 |  | All | Standard pre-cutover checklist maintained in the approved cutover runbook; test certificate chain in non-prod | Not Started | Green
D-08 | Technical | PostgreSQL version / extension / role compatibility with the chosen managed service; storage limits vs largest DBs | DBA Lead | LZ-08 | Managed PostgreSQL pattern: HA, automated backup, PITR, cross-region replica, CMEK | 2 | 2026-10-19 | 2 | 0 | 2026-10-05 | START AT KICKOFF | All DB moves | DS-04 profiling; compatibility test in sandbox; fall back to self-managed PostgreSQL for exceptions | Not Started | Amber
D-09 | Technical | Secrets, keys and certificates migration (CMEK/KMS, HSM-backed keys where required) | Security Lead | LZ-04 | Security controls: CMEK/KMS, secrets management, SIEM logging, vulnerability scanning | 2 | 2026-10-19 | 2 | 0 | 2026-10-05 | START AT KICKOFF | All | Secrets inventory in discovery; no secrets in images; rotate at cutover | Not Started | Amber
D-10 | Technical | Integration with enterprise SIEM, ITSM and monitoring tools | SRE / Security | LZ-05 | Observability: monitoring, logging, tracing, alerting, SLO dashboards | 2 | 2026-10-19 | 1 | 1 | 2026-10-12 | START AT KICKOFF | All | Agree log/metric export design in DS-07; test alert routing in pilot | Not Started | Green
D-11 | Technical | Masked, prod-like test data available for non-prod testing | QA Lead / DBA Lead | PL-05 | Functional and regression testing (incl. batch scheduling) | 5 | 2026-11-09 | 3 | 2 | 2026-10-19 | START IN MONTH 1 | All | Data-masking pipeline built with LZ-09; privacy sign-off | Not Started | Amber
D-12 | Technical | Batch scheduler integration (job dependencies, calendars, re-run behaviour) | App Teams / Ops | PL-03 | Deploy to GCP non-prod; secrets/config onboarding; observability wiring | 5 | 2026-11-09 | 3 | 2 | 2026-10-19 | START IN MONTH 1 | Pilot, W1, W3 | Pilot batch app proves the pattern; document re-run/restart procedures | Not Started | Amber
D-13 | Technical | Windows licensing and Windows-node support for .NET Framework workloads (containers or GCE) | Platform Lead / Procurement | LZ-06 | Compute platform build (per ADR), registry, Windows node pool if required | 2 | 2026-10-19 | 2 | 0 | 2026-10-05 | START AT KICKOFF | Wave 2 | Decide container vs VM in DS-06; confirm licence mobility early | Not Started | Amber
D-14 | Organizational | Security sign-off of the landing zone (pen-test, control mapping) | Security Lead | GATE-M1 | M1: FOUNDATION READY (approver: Security + Platform) | 4 | 2026-11-02 | 4 | 0 | 2026-10-05 | START AT KICKOFF | All | Security engineer embedded in platform team; weekly security review; pre-agreed patterns | Not Started | Amber
D-15 | Organizational | GCP quotas (vCPU, IPs, DB instances) raised ahead of peak waves | Platform Lead / Google TAM | W2-04 | Deploy to non-prod and integration environments (shared-DB test) | 9 | 2026-12-07 | 4 | 5 | 2026-11-09 |  | Waves 2-3 | Request quota increases at M1 and again before Wave 2 and Wave 3 non-prod | Not Started | Green
D-16 | Organizational | CAB slots and change-freeze calendar for every production cutover | Change Manager | PL-08 | PILOT PRODUCTION CUTOVER (3 apps) | 7 | 2026-11-23 | 4 | 3 | 2026-10-26 | START IN MONTH 1 | All | Book all cutover slots in PM-04; check Freeze Check column on Roadmap | Not Started | Amber
D-17 | Organizational | Environment provisioning requests through ITSM (non-prod, UAT, access) | Platform Lead | PL-03 | Deploy to GCP non-prod; secrets/config onboarding; observability wiring | 5 | 2026-11-09 | 3 | 2 | 2026-10-19 | START IN MONTH 1 | All | Pre-raise requests for every wave in PM-03; use IaC for self-service | Not Started | Amber
D-18 | Organizational | SME backfill - application SMEs and DBAs released from BAU | App Owners / Hiring managers | W2-02 | Containerise / limited refactor of 4 apps (2 Refactor, 2 Replatform) | 6 | 2026-11-16 | 6 | 0 | 2026-10-05 | START AT KICKOFF | Waves 2-3 | Backfill approved in PM-03; resource loading reviewed monthly | Not Started | Red
D-19 | Organizational | Business UAT availability and sign-off (esp. Tier 1) | Business owners / Change Manager | W1-04 | Functional, regression, performance and security testing | 6 | 2026-11-16 | 4 | 2 | 2026-10-19 | START IN MONTH 1 | All | UAT windows booked at wave plan approval; delegate approvers named | Not Started | Amber
D-20 | Organizational | Funding release, billing account and GCP commitment in place | Finance / Executive Sponsor | LZ-01 | Org hierarchy, projects/folders, org policies, billing and budget alerts | 1 | 2026-10-12 | 2 | -1 | 2026-09-28 | START AT KICKOFF | All | Confirm at kickoff (assumption in program plan) | Not Started | Green
D-21 | Organizational | Third-party / vendor-risk assessment of GCP services in scope | Compliance / Procurement | GATE-M1 | M1: FOUNDATION READY (approver: Security + Platform) | 4 | 2026-11-02 | 6 | -2 | 2026-09-21 | START AT KICKOFF | All | Start at kickoff; reuse existing cloud risk assessments where possible | Not Started | Amber
D-22 | Organizational | SRE training and on-call onboarding for new platform | SRE Lead | FN-04 | SRE handoff: runbook validation, on-call readiness, support model, incident process | 22 | 2027-03-08 | 8 | 14 | 2027-01-11 |  | All | SRE engaged from Month 1; shadow on-call from pilot | Not Started | Green
D-23 | Organizational | Pilot gate (M2) approved before any wave production cutover (Non-negotiable #2) | Steering Committee | W1-08 | WAVE 1 PRODUCTION CUTOVER (5 apps) - before year-end freeze | 10 | 2026-12-14 | 0 | 10 | 2026-12-14 |  | Waves 1-3 | Pilot go/no-go criteria agreed at M1; retro feeds Wave 1 runbooks | Not Started | Green
D-24 | External | Third-party vendors / partners must allow-list new GCP egress IPs and accept changed endpoints | Vendor Management | W1-08 | WAVE 1 PRODUCTION CUTOVER (5 apps) - before year-end freeze | 10 | 2026-12-14 | 6 | 4 | 2026-11-02 | START IN MONTH 1 | All | Reserve static egress IPs early; send change notices at wave plan approval | Not Started | Amber
D-25 | External | Regulatory notification / approval for material cloud outsourcing (as applicable to your regulator) | Compliance / Legal | GATE-PILOT | PILOT GO-LIVE approval (approver: Steering Committee) + CAB | 6 | 2026-11-16 | 8 | -2 | 2026-09-21 | START AT KICKOFF | All | Confirm obligations at kickoff (PM-05); start any pre-notification immediately | Not Started | Red
D-26 | External | Google Cloud account team: support tier, TAM, quota escalations, architecture review | Vendor Management | LZ-01 | Org hierarchy, projects/folders, org policies, billing and budget alerts | 1 | 2026-10-12 | 2 | -1 | 2026-09-28 | START AT KICKOFF | All | Engage at kickoff; named escalation contacts | Not Started | Green
D-27 | External | Legacy platform contracts, leases and exit-notice periods (needed for decommission in Month 6) | Procurement / Infrastructure | FN-06 | Decommission readiness review (zero traffic, no consumers, contract / lease notices) | 23 | 2027-03-15 | 16 | 7 | 2026-11-23 |  | All | Review contracts in Month 1; serve notices when waves complete | Not Started | Red
D-28 | External | ISV / third-party software licensing and cloud support statements | Procurement | W2-03 | Rehost 2 legacy .NET apps to GCE Windows VMs | 7 | 2026-11-23 | 4 | 3 | 2026-10-26 | START IN MONTH 1 | Wave 2 | Inventory ISV components in DS-02; confirm supported on GCE / containers | Not Started | Amber
D-29 | External | Customer / partner communications for Tier-1 downtime windows | Business owners / Comms | W3-11 | CUTOVER 3b: Tier-1 apps (3 apps) - final production cutover | 19 | 2027-02-15 | 6 | 13 | 2027-01-04 |  | Wave 3 | Agree notice periods in contracts; schedule outside business peaks | Not Started | Amber

## RAID Register
Top 15 Program Risks
ID | Category | Risk | Impact | Linked Tasks | Score | RAG | Mitigation | Contingency | Early Warning | Owner | Due Week | Residual RAG | Escalation Path | Status
R-01 | Schedule | Hidden / unmapped dependencies surface late | Schedule delay; failed cutover; wave re-plan | All waves; DS-03 | 16 | Red | Discovery workshops; network-flow capture on legacy (>= 30 days); weekly Dependency Review Board; dependency freeze at wave plan approval | Add coexistence connectivity; hold wave until dependency resolved | > 2 new dependencies found per wave after plan lock | TPM | 4 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-05 | Infrastructure | Hybrid network capacity or provisioning delays | Replication cannot keep pace; waves slip | LZ-03, LZ-09; Waves 2-3 | 16 | Red | Order circuits at kickoff; HA VPN interim; redundant paths; throttling plan; replication throughput test at W3-4 | Offline transfer appliance for bulk seed; re-sequence large DBs | Circuit delivery date slips beyond W4 | Platform Lead | 2 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-07 | Resource | Resource constraints: SMEs, DBAs, SRE oversubscribed across overlapping waves | Reduced throughput; quality shortcuts | W9-W17 | 16 | Red | Resource-loading plan per wave; backfill approved at kickoff; dedicated migration capacity; deputy / PMO analyst for TPM | Re-sequence Wave 3 prep; defer non-critical refactors | Utilisation > 90% for key roles; stand-ups reporting blocked on people | TPM | 3 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-12 | Technical | Shared-DB coupling forces multi-app big-bang cutovers in Wave 2 | Larger blast radius; harder rollback | Wave 2 | 16 | Red | Group cutovers by DB; split into 2a / 2b; decouple through APIs where cheap; 2 full rehearsals | Postpone coupled apps to later window; extended rollback window | Rehearsal #1 fails or exceeds window | Cloud Architect / DBA Lead | 3 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-29 | Technical | Data volume back-loaded into Wave 3; replication seeding overlaps Wave 2 on the same hybrid link | Replication cannot catch up; cutover delay | W2-05, W3-04 | 16 | Red | Start Wave 3 seeding for largest DBs as early as safe; schedule bandwidth; QoS on link; consider offline seed | Delay 3b; split DB cutovers | Replication lag trend > 10 min after seeding | DBA Lead / Platform Lead | 3 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-03 | Data | Data loss or corruption during migration of tens of TB | Customer / regulatory impact; program failure | All DB moves | 15 | Red | Continuous replication with lag monitoring; counts + checksums + reconciliation; 2 rehearsals; cutover only when lag < agreed threshold | Roll back to legacy using reverse replication; restore from PITR | Replication lag trend rising; reconciliation variance > 0 | DBA Lead | 4 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-09 | Resilience | DR targets not achieved (RPO <= 5 min, RTO <= 60 min, 99.95% availability) | Program failure / M2, M6 not met | PL-10; W*-DR tests; FN-01 | 15 | Red | DR topology ADR at W2; DR tests in pilot and every wave; automate failover; measure RPO/RTO each test | Upgrade DB tier / replication mode; add warm standby; re-test | Measured RPO or RTO > 80% of target in any test | SRE Lead / DBA Lead | 4 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-13 | Technical | Rollback after DB cutover is complex (data written in GCP) | Extended outage; data divergence | All cutovers | 15 | Red | Define rollback policy and point of no return per wave (DEC-08); reverse replication; rollback rehearsal; time-boxed decisions | Forward-fix with war-room authority; restore from PITR | Rollback rehearsal exceeds RTO | DBA Lead / SRE Lead | 3 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-02 | Technical | Legacy .NET Framework apps not container-compatible | Migration delay; rework | Wave 2 (rehost); DS-06 | 12 | Amber | Early PoC (DS-06); 2 apps already planned as Rehost; Windows node pool / GCE fallback | Rehost on GCE Windows VMs | PoC fails or needs > 2 weeks of rework per app | Cloud Architect | 5 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-04 | Technical | PostgreSQL incompatible with managed service (version, extensions, privileges, storage limits) | Redesign; delay; cost | LZ-08; all DBs | 12 | Amber | DS-04 profiling; compatibility test in sandbox; DB service ADR at W2 | Self-managed PostgreSQL on GCE for exceptions; shard / archive large DBs | Any unsupported extension in profiling output | DBA Lead | 3 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-06 | Security | Security approval delays / findings block landing zone or releases | Release blockage; M1 slips | GATE-M1; all waves | 12 | Amber | Security embedded from Day 1; pre-approved patterns; weekly security review; findings triaged by severity | Time-boxed exception process with compensating controls | > 3 high findings open one week before M1 | Security Lead | 4 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-10 | Schedule | Year-end / quarter-end freezes and holidays compress cutover windows | Cutover slips by 3-4 weeks; Month-3 milestone missed | PL-08, W1-08, W2-10 | 12 | Amber | Freeze calendar maintained in the program change calendar; Wave 1 cutover scheduled before freeze; hypercare spans the freeze | Use cutover contingency week; move pilot cutover to Mon-Tue of W7 | Any planned cutover or DR test overlaps an approved freeze window | Change Manager | 1 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-11 | Schedule | Compressed end-game: Tier-1 cutover in W19 leaves ~7 weeks to M6; Tier-1 hypercare may need extension | M6 / decommission slips | W3-11, W3-12; Month 6 | 12 | Amber | Two rehearsals for Tier 1; extended hypercare allowance; M6 phase has buffer (W22-26); agreed decision points | Defer decommission of last platform; extend hypercare | Sev-1 during Wave 3 hypercare; rehearsal rollback > 60 min | TPM | 3 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-14 | Performance | Latency / throughput regression after migration | SLO breach; user complaints | All waves | 12 | Amber | Legacy baseline (DS-08); load tests; keep dependent apps in same wave; autoscaling tuned in non-prod | Scale up; tune queries; roll back | p95 latency > baseline + 20% in test | SRE Lead / QA Lead | 2 | Amber | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open
R-15 | Compliance | Regulatory notification / approval delays or audit evidence gaps | Go-live blocked; audit findings | GATE-PILOT; FN-08 | 12 | Amber | PM-05 regulatory plan at kickoff; evidence captured continuously (LZ-10); compliance in SteerCo | Escalate to Executive Sponsor / Legal; adjust wave dates | No regulator acknowledgement 6 weeks before Pilot Go-Live | TPM / Compliance | 2 | Green | Owner -> TPM -> Steering Committee -> Executive Sponsor | Open